## Sheet1
Cost Estimate
Project Name: Health App |  |  |  | Date: 08/23/2020
WBS Categories | Total Team Cost($) | hours per week(hrs) | Total cost per week($) | Total cost for six sprints($)
1. Initiating | 340 | 8 | 2720 | 32640
2. Planning | 340 | 10 | 3400 | 40800
3. Designing | 340 | 12 | 4080 | 48960
3.1 UI Design |  | 3 | 0 | 0
3.2 Synthesis of Design |  | 3 |  | 0
3.3 Iteration Execution |  | 3 | 0 | 0
3.4 Contract finalization and release |  | 3 | 0 | 0 | Designation | $/hour
4. Implementation | 340 | 12 | 4080 | 48960 | Team Leader | 65
4.1 Application Development |  | 3 | 0 | 0 | Project Manager | 75
4.2 PWA Execution |  | 3 | 0 | 0 | Full stack Developer | 70
4.3Application Implementation |  | 3 | 0 | 0 | Front end Developer | 60
5. Monitoring and Controlling | 340 | 10 | 3400 | 40800 | Database Engineer | 70
6. Closing | 340 | 11 | 3740 | 44880 |  | 340
Total |  |  |  | 257040